## Worksheet
Task ID | Created At | Completed At | Last Modified | Name | Section/Column | Assignee | Assignee Email | Start Date | Due Date | Tags | Notes | Projects | Parent Task | Blocked By (Dependencies) | Blocking (Dependencies) | PIC Dept | Plan Man Days | Actual Start Date | Actual Finish Date | Actual Man Days | Status | Progress | Keterangan
1202602865052816 | 2022-07-14 |  | 2022-08-18 | Start Development | Untitled section | Riki Sholiardi | riki@dbc.co.id |  |  |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev
1202730782921292 | 2022-08-06 | 2022-08-24 | 2022-08-24 | Pembuatan Tampilan Menu Master Sub Account | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 2022-08-22 | 2022-08-24 | 2 | Done | 1
1202730782921294 | 2022-08-06 | 2022-08-24 | 2022-08-24 | Pembuatan Tampilan Menu Master Invoice Status | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 2022-08-22 | 2022-08-24 | 2 | Done | 1
1202730782921296 | 2022-08-06 | 2022-08-30 | 2022-08-30 | Pembuatan Tampilan Menu Master Pembayaran | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 2022-08-25 | 2022-08-26 | 2 | Done | 1
1202730782921298 | 2022-08-06 | 2022-08-30 | 2022-08-30 | Pembuatan Tampilan Menu Transaksi Outstanding Tanda Terima | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 3 | 2022-08-25 | 2022-08-26 | 2 | Done | 1
1202730782921300 | 2022-08-06 | 2022-08-31 | 2022-09-08 | Pembuatan Tampilan Menu Transaksi Outstanding Tanda Terima - Detail | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 3 | 2022-08-29 | 2022-08-30 | 2 | Done | 1
1202730782921308 | 2022-08-06 | 2022-08-31 | 2022-09-08 | Pembuatan Tampilan Menu Transaksi Outstanding Tanda Terima - Detail Invoice (Inputan) | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-09-06 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 3 | 2022-08-29 | 2022-08-30 | 2 | Done | 1
1202730782921302 | 2022-08-06 | 2022-09-02 | 2022-09-08 | Pembuatan Tampilan Menu Transaksi Outstanding Tanda Terima - List PO & MMR | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-09-06 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 3 | 2022-08-31 | 2022-09-01 | 2 | Done | 1
1202730782921310 | 2022-08-06 | 2022-09-02 | 2022-09-08 | Penambahan kolom keterangan revisi pada Menu List Tagihan Finance | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 3 | 2022-08-31 | 2022-09-01 | 2 | Done | 1
1202730782921304 | 2022-08-06 | 2022-09-06 | 2022-09-08 | Pembuatan Tampilan Menu Transaksi Outstanding Tanda Terima - Preview Tab Invoice & PO | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 3 | 2022-09-02 | 2022-09-06 | 2 | Done | 1
1202730782921306 | 2022-08-06 | 2022-09-06 | 2022-09-08 | Pembuatan Tampilan Menu Transaksi Outstanding Tanda Terima - Preview Tab Detail | Untitled section | Diana Asikin | diana@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 3 | 2022-09-02 | 2022-09-06 | 2 | Done | 1
1202825219721255 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller Filter Sub Account (Sub Account) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721257 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller View Sub Account (Sub Account) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721259 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller Sync Sub Account (Sub Account) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721261 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller Filter Invoice Status (Invoice Status) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721263 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller View Invoice Status (Invoice Status) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721265 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller Sync Invoice Status (Invoice Status) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721267 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller Filter Kode (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721269 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller Filter No. Rekening (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721271 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller Filter Nama Bank (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721273 | 2022-08-19 | 2022-08-22 | 2022-08-22 | Pembuatan Controller View Master Pembayaran (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-22 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 22/08/2022 | 22/08/2022 | 1 | Done | 1
1202825219721275 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Sync Master Pembayaran (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721277 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Filter No. Tagihan (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721279 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Filter Tanda Terima (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721281 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Filter Bisnis Unit (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721283 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Filter Site (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721285 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Filter Vendor (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721287 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Filter No. PO (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721289 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Filter Eks/Int (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721291 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Filter Status (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721293 | 2022-08-19 | 2022-08-23 | 2022-08-23 | Pembuatan Controller Filter Tgl. Jatuh Tempo Awal (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 23/08/2022 | 23/08/2022 | 1 | Done | 1
1202825219721295 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller View List Main (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721297 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller Button Download (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721299 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller View No. Tagihan (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721301 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller View Tanda Terima (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721303 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller View Bisnis Unit (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721305 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller View Site (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721307 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller View Vendor (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721309 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller View Curr (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721311 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller View Eks/Int (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721313 | 2022-08-19 | 2022-08-25 | 2022-08-25 | Pembuatan Controller View Jatuh Tempo (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-24 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 24/08/2022 | 24/08/2022 | 1 | Done | 1
1202825219721315 | 2022-08-19 | 2022-08-25 | 2022-08-26 | Pembuatan Controller View List Second (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 1
1202825219721317 | 2022-08-19 | 2022-08-26 | 2022-09-02 | Pembuatan Controller Gabungan Upload QAD (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 10
1202825219721319 | 2022-08-19 | 2022-08-26 | 2022-09-02 | Pembuatan Controller Input Reason Reject (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 1
1202825219721321 | 2022-08-19 | 2022-08-26 | 2022-08-26 | Pembuatan Controller View List Third (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 1
1202825219721323 | 2022-08-19 | 2022-08-26 | 2022-08-26 | Pembuatan Controller Button Reject (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 1
1202825219721325 | 2022-08-19 | 2022-08-26 | 2022-08-26 | Pembuatan Controller Kolom Keterangan Revisi (List Tagihan Finance) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 1
1202825219721327 | 2022-08-19 | 2022-08-26 | 2022-08-26 | Pembuatan Controller Input Reference (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 1
1202825219721329 | 2022-08-19 | 2022-08-26 | 2022-08-26 | Pembuatan Controller Input Description (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 1
1202825219721331 | 2022-08-19 | 2022-08-26 | 2022-08-26 | Pembuatan Controller Input Invoice Date (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 1
1202825219721333 | 2022-08-19 | 2022-08-26 | 2022-08-26 | Pembuatan Controller Input Posting Date (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-25 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 25/08/2022 | 25/08/2022 | 1 | Done | 1
1202825219721335 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Input TC Inv Amount (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721337 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Input Mata Uang (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721339 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Taxable (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721341 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Input Inv Status (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721343 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Input Sub Account (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721345 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Input No. Faktur Pajak (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721347 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Input Tgl. Faktur Pajak (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721349 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Input Tuj. Bayar 1 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721351 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Input Tuj. Bayar 2 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721353 | 2022-08-19 | 2022-08-28 | 2022-08-28 | Pembuatan Controller Input Tuj. Bayar 3 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 26/08/2022 | 26/08/2022 | 1 | Done | 1
1202825219721355 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Input Tuj. Bayar 4 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721357 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Input Tuj. Bayar 5 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721359 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Input Tuj. Bayar 6 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721361 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Input Bank Pengirim (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721363 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Input Bank Account (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721365 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Input Comment (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721367 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Button Submit (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721369 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Input Reference (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721371 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Input Description (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721373 | 2022-08-19 | 2022-08-30 | 2022-09-02 | Pembuatan Controller Input Invoice Date (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 29/08/2022 | 29/08/2022 | 1 | Done | 1
1202825219721375 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Posting Date (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721377 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input TC Inv Amount (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721379 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Mata Uang (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721381 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Taxable (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721383 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Inv Status (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721385 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Sub Account (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721387 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input No. Faktur Pajak (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721389 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Tgl. Faktur Pajak (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721391 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Tuj. Bayar 1 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721393 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Tuj. Bayar 2 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 30/08/2022 | 30/08/2022 | 1 | Done | 1
1202825219721395 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Tuj. Bayar 3 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721397 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Tuj. Bayar 4 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721399 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Tuj. Bayar 5 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721401 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Tuj. Bayar 6 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721403 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Bank Pengirim (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721405 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Bank Account (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721407 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Input Comment (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721409 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller Button Submit (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721411 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan XML Create Supplier Invoice | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721413 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller View No. Tagihan (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-08-31 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 31/08/2022 | 31/08/2022 | 1 | Done | 1
1202825219721415 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller View Tanda Terima (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-01 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 01/09/2022 | 01/09/2022 | 1 | Done | 1
1202825219721417 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller View Bisnis Unit (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-01 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 01/09/2022 | 01/09/2022 | 1 | Done | 1
1202825219721419 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller View Site (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-01 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 01/09/2022 | 01/09/2022 | 1 | Done | 1
1202825219721421 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller View Vendor (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-01 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 01/09/2022 | 01/09/2022 | 1 | Done | 1
1202825219721423 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller View Curr (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-01 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 01/09/2022 | 01/09/2022 | 1 | Done | 1
1202825219721425 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller View Eks/Int (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-01 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 01/09/2022 | 01/09/2022 | 1 | Done | 1
1202825219721427 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller View Jatuh Tempo (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-01 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 01/09/2022 | 01/09/2022 | 1 | Done | 1
1202825219721429 | 2022-08-19 | 2022-09-02 | 2022-09-02 | Pembuatan Controller View List Fourth (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-01 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 01/09/2022 | 01/09/2022 | 1 | Done | 1
1202825219721431 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller View User (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721433 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller View Date Revisi (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721435 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller View Reason (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721437 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller View Reference (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721439 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller View Description (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721441 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller View Invoice Date (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721443 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller View Posting Date (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721445 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller View TC Inv Amount (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721447 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller View Mata Uang (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721449 | 2022-08-19 | 2022-09-05 | 2022-09-05 | Pembuatan Controller Taxable (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-02 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 02/09/2022 | 02/09/2022 | 1 | Done | 1
1202825219721451 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View Inv Status (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721453 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View Sub Account (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721455 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View No. Faktur Pajak (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721457 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View Tgl. Faktur Pajak (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721459 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View Tuj. Bayar 1 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721461 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View Tuj. Bayar 2 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721463 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View Tuj. Bayar 3 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721465 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View Tuj. Bayar 4 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721467 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View Tuj. Bayar 5 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721469 | 2022-08-19 | 2022-09-06 | 2022-09-06 | Pembuatan Controller View Tuj. Bayar 6 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-05 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 05/09/2022 | 05/09/2022 | 1 | Done | 1
1202825219721471 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan Controller View Bank Pengirim (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-06 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 06/09/2022 | 06/09/2022 | 1 | Done | 1
1202825219721473 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan Controller View Bank Account (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-06 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 06/09/2022 | 06/09/2022 | 1 | Done | 1
1202825219721475 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan Controller View Comment (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-06 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 06/09/2022 | 06/09/2022 | 1 | Done | 1
1202825219721477 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan Controller View Invoice To Upload (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-06 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 06/09/2022 | 06/09/2022 | 1 | Done | 1
1202825219721479 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan XML Re-Create Supplier Invoice | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-06 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 06/09/2022 | 06/09/2022 | 1 | Done | 1
1202825219721481 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan Controller Button Close (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721483 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Sub Account (Sub Account) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721485 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery View Sub Account (Sub Account) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721487 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Sync Sub Account (Sub Account) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721489 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Invoice Status (Invoice Status) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721491 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery View Invoice Status (Invoice Status) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721493 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Sync Invoice Status (Invoice Status) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721495 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Kode (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721497 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter No. Rekening (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721499 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Nama Bank (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-07 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 07/09/2022 | 07/09/2022 | 1 | Done | 1
1202825219721501 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery View Master Pembayaran (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721503 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Sync Master Pembayaran (Master Pembayaran) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721505 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter No. Tagihan (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721507 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Tanda Terima (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721509 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Bisnis Unit (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721511 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Site (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721513 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Vendor (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721515 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter No. PO (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721517 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Eks/Int (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721519 | 2022-08-19 | 2022-09-09 | 2022-09-09 | Pembuatan JQuery Filter Status (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-08 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 | 08/09/2022 | 08/09/2022 | 1 | Done | 1
1202825219721521 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery Filter Tgl. Jatuh Tempo Awal (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721523 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery View List Main (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721525 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery Button Download (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721527 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery View No. Tagihan (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721529 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery View Tanda Terima (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721531 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery View Bisnis Unit (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721533 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery View Site (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721535 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery View Vendor (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721537 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery View Curr (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721539 | 2022-08-19 |  | 2022-09-09 | Pembuatan JQuery View Eks/Int (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-09 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721541 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Jatuh Tempo (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-12 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721543 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View List Second (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-12 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721545 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Gabungan Upload QAD (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-12 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721547 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Reason Reject (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-12 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721549 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View List Third (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-12 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721551 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Button Go To Details (Outstanding Tanda Terima) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-13 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721553 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Kolom Keterangan Revisi (List Tagihan Finance) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-13 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721555 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Reference (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-13 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721557 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Description (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-13 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721559 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Invoice Date (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-13 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721561 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Posting Date (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721563 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input TC Inv Amount (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721565 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Mata Uang (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721567 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Taxable (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721569 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Inv Status (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721571 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Sub Account (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721573 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input No. Faktur Pajak (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721575 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tgl. Faktur Pajak (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721577 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 1 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721579 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 2 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-14 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721581 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 3 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-15 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721583 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 4 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-15 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721585 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 5 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-15 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721587 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 6 (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-15 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721589 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Bank Pengirim (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-15 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721591 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Bank Account (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-15 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721593 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Comment (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-15 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721595 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Button Submit (Supplier Invoice Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-16 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721597 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Reference (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-16 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721599 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Description (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-16 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721601 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Invoice Date (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-16 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721603 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Posting Date (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-16 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721605 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input TC Inv Amount (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-16 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721607 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Mata Uang (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-16 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721609 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Taxable (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-19 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721611 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Inv Status (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-19 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721613 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Sub Account (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-19 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721615 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input No. Faktur Pajak (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-19 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721617 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tgl. Faktur Pajak (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-19 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721619 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 1 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-19 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721621 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 2 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-19 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721623 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 3 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-20 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721625 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 4 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-20 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721627 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 5 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-20 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721629 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Tuj. Bayar 6 (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-20 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721631 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Bank Pengirim (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-20 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721633 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Bank Account (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-20 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721635 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Input Comment (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-20 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721637 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Button Submit (Supplier Invoice Non. Gabungan) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-21 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721639 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View No. Tagihan (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-21 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721641 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Tanda Terima (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-21 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721643 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Bisnis Unit (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-21 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721645 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Site (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-21 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721647 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Vendor (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721649 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Curr (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721651 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Eks/Int (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721653 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Jatuh Tempo (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-23 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721655 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View List Fourth (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721657 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View User (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721659 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Date Revisi (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721661 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Reason (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721663 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Reference (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-26 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721665 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Description (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-27 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721667 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Invoice Date (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-27 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721669 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Posting Date (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-27 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721671 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View TC Inv Amount (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-27 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721673 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Mata Uang (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-27 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721675 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Taxable (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-28 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721677 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Inv Status (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-28 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721679 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Sub Account (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-28 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721681 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View No. Faktur Pajak (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-28 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721683 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Tgl. Faktur Pajak (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-28 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721685 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Tuj. Bayar 1 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-28 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721687 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Tuj. Bayar 2 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-28 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721689 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Tuj. Bayar 3 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721691 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Tuj. Bayar 4 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721693 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Tuj. Bayar 5 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721695 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Tuj. Bayar 6 (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721697 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Bank Pengirim (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-29 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721699 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Bank Account (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721701 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Comment (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721703 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery View Invoice To Upload (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202825219721705 | 2022-08-19 |  | 2022-08-19 | Pembuatan JQuery Button Close (Preview Supplier Invoice) | Untitled section | Riki Sholiardi | riki@dbc.co.id |  | 2022-09-30 |  |  | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev |  |  |  | Development | 2 |  |  |  | Not Started | 0
1202430278663975 | 2022-06-11 |  | 2022-06-11 | Serah terima Dev ke QC | Untitled section | [6 empty] | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev
1202430278667524 | 2022-06-11 |  | 2022-06-11 | Dokumen Serah Terima Dev ke QC | Untitled section | [6 empty] | 22-022-Improvement Finance System (otomatis create supplier invoice - Monitoring,22-022-Improvement Finance System (otomatis create supplier invoice - Dev